## POA&M
Plan of Action and Milestones (POA&M) — CloudSync Solutions — TPRM-2025-007
Analyst: Lazaro Denis ¦ Issued: March 19, 2025 ¦ Review Cycle: Quarterly
POA&M ID | Finding ID | Risk ID | Gap Description | Required Action | Owner | Priority | Target Date | Status | Compensating Control | Notes
POA&M-001 | FIND-001 | RISK-001 | MFA not required for all users accessing Meridian data | Mandate MFA for all CloudSync users with access to Meridian tenant. Enforce at SSO/SAML layer or platform-wide. Provide written confirmation and screenshot evidence. | CloudSync Security Team | High | June 30, 2025 | Not Started | Meridian to enforce MFA via Azure AD Conditional Access before go-live | Conditional approval contingent on interim compensating control before go-live
POA&M-002 | FIND-002 | RISK-002 | PII present in non-production environments; no data masking policy | Implement formal data masking policy. Use synthetic data in all dev/test environments. Provide written policy and implementation evidence. | CloudSync Security Team | High | August 31, 2025 | Not Started | No Meridian production data to flow to CloudSync non-prod environments | Confirmed with HR and IT before go-live
POA&M-003 | FIND-003 | RISK-003 | DLP coverage limited to outbound email; no API or bulk-export DLP | Expand DLP to cover API exports and cloud storage. Implement alerting for anomalous bulk data egress events. Provide roadmap with committed dates. | CloudSync Security Team | Medium | December 31, 2025 | Not Started | Restrict Meridian admin export permissions to minimum necessary | CloudSync evaluating CASB/DLP tooling; no firm date yet
POA&M-004 | FIND-004 | RISK-005 | Contract limits audit rights to SOC 2 review only | Negotiate contract amendment to allow annual questionnaire re-assessment and right to request supplemental evidence at Meridian's cost. | Meridian Legal / GRC | Low | April 30, 2025 | Not Started | N/A | CloudSync expressed openness to questionnaire re-assessment clause
POA&M-005 | FIND-005 | RISK-006 | Sub-processor list not independently reviewed by Meridian | Obtain CloudSync's sub-processor list. Confirm DPAs in place. Add change-notification clause to contract. | Meridian GRC / Legal | Low | April 30, 2025 | Not Started | N/A | Sub-processor list available per vendor; DPAs confirmed verbally
STATUS LEGEND
🔴 Not Started | No action taken | 🟡 In Progress | Remediation underway | 🟢 Completed | Control implemented and verified | 🔵 Monitoring | Ongoing monitoring in place | ⚪ Accepted | Risk accepted; no remediation required

## Milestone Timeline
POA&M Milestone Timeline — TPRM-2025-007
Phase | Milestone | Owner | Target Date | POA&M Ref | Priority
Pre-Go-Live | Enforce MFA via Azure AD Conditional Access | Meridian IT | Before April 1, 2025 | POA&M-001 (interim) | High
Pre-Go-Live | Execute HIPAA BAA | Meridian Legal | Before April 1, 2025 | — | High
Pre-Go-Live | Confirm no Meridian prod data in CloudSync non-prod | Meridian GRC / HR | Before April 1, 2025 | POA&M-002 (interim) | High
Contract | Negotiate audit rights and sub-processor clause | Meridian Legal | April 30, 2025 | POA&M-004, 005 | Low
Contract | Obtain sub-processor list and DPA confirmation | Meridian GRC | April 30, 2025 | POA&M-005 | Low
Remediation | CloudSync mandates MFA for all users | CloudSync | June 30, 2025 | POA&M-001 | High
Remediation | POA&M-001 close-out evidence reviewed by GRC | Lazaro Denis | July 15, 2025 | POA&M-001 | High
Remediation | CloudSync implements data masking policy for non-prod | CloudSync | August 31, 2025 | POA&M-002 | High
Remediation | POA&M-002 close-out evidence reviewed by GRC | Lazaro Denis | September 15, 2025 | POA&M-002 | High
Remediation | CloudSync expands DLP to API/cloud storage | CloudSync | December 31, 2025 | POA&M-003 | Medium
Remediation | POA&M-003 progress check | Lazaro Denis | January 15, 2026 | POA&M-003 | Medium
Annual | Full annual vendor reassessment | GRC Team | March 2026 | All | —